## TestScenarios
Project Name | Banking System
Reference Document
Created By | Akram Khan
Creation Date | 2025-04-07
Approval Date | 2025-04-07
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the working of the "Deposit" functionality. | P0
TS_002 |  | Validate the "Withdrawals" functionality | P0
TS-003 |  | Validate the "Transfer" functionality | P0
TS_004 |  | Validate the "Add Interest " functionality | P1
TS_005 |  | Validate the "Reset Account" functionality | P2
TS_006 |  | Validate the " Transfer History" functionality | P1
TS_006 |  | Validate the " Transaction History" functionality | P1
TS_007 |  | Validate the " Filter Transactions" functionality

## TestCase
Product Name |  |  | TC Start Date | 2025-04-08 | TC Execution Start Date | 2025-04-11 |  |  |  |  | TEST CASE
Module Name |  |  | TC End Date | 2025-04-10 | TC Execution End Date | 2025-04-11 |  |  |  |  | PASS | 62
Epic |  |  | Test Case Developed By | Akram Khan | Browser (tested) | Yes |  |  |  |  | FAIL | 1
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 63
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 |  |  | User | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search testing-and-learning-hub.vercel.app' 3. Go to the website. |  |  | Passed
2 | Transactions |  | Deposit | Checking spelling or gramatical mistake | No spelling or grammatical mistakes | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Verifying the font, text color and style | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
|  |  |  | Checking Number Input Spinner is working | Should increase or decrease the entered amout | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
|  |  |  | Deposit Button is Clickable | Should be clickable | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
5 |  |  |  | Inputing Amount with special characters | Should not accept the provided input | Found as per expectation. | "*&&&*()))) **###@%%" | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
|  |  |  | Checking input fiield as blank | Should provide an error message | Found as per expectation. |  | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
6 |  |  |  | Inputing amount with alphanumeric characters | Should not accept the provided input | Found as per expectation. | 1o10 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
7 |  |  |  | Inputing amount with decimal numbers | Should accept the provided input | Found as per expectation. | 1000.01 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
8 |  |  |  | Verify deposit with valid amount | Should accept the provided input | Found as per expectation. | 1000 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
9 |  |  |  | Deposit with zero amount | Should provide an error message | Found as per expectation. | 0 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
10 |  |  |  | Deposit with negative amount | Should provide an error message | Found as per expectation. | -100 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
11 |  |  |  | Deposit with invalid input | Should provide an error message | Found as per expectation. | abc | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
12 |  |  |  | Verify deposit with valid amount | Should provide successful message | Found as per expectation. | 1000 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
18
19
20 |  |  | Withdraw | Withdraw Button is Clickable | Should be clickable | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
21 |  |  |  | Withdraw with valid amount | Balance should be decreases by 500 | Found as per expectation. | 500 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
22 |  |  |  | Withdraw more than available balance | Should provide an error message | Found as per expectation. | 700 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
23 |  |  |  | Withdraw with zero/negative amount | Should provide an error message | Found as per expectation. | 0 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
24 |  |  |  | Withdraw with negative amount | Should provide an error message | Found as per expectation. | -1 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
25 |  |  |  | Withdraw amount with decimal numbers | Balance should be decreases | Found as per expectation. | 200.01 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
26 |  |  |  | Inputing amount with alphanumeric characters | Should provide an error message | Found as per expectation. | abc | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on amount in transactions section |  |  | Passed
39
40 |  |  | Transfer | Transfer Button is Clickable | Should be clickable | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button |  |  | Passed
|  |  |  | Enter invalid account number | Should provide an error message | Found as per expectation. | asdasdasdad | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button 4.Enter account number 5.Click Ok |  |  | Passed
|  |  |  | Enter valid account number but not User 2 | Should provide an error message | Found as per expectation. | 2301456789 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button 4.Enter account number 5.Click Ok |  |  | Passed
41 |  |  |  | Transfer valid amount to but not existing account | Should not be decrease from current account | Found as per expectation. | 200/1023456789 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button 4.Enter account number 5.Click Ok |  |  | Passed
42 |  |  |  | Transfer valid amount to existing account | Should be increase user2 account | Found as per expectation. | 200 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button 4.Enter account number 5.Click Ok |  |  | Passed
43 |  |  |  | Transfer with insufficient balance | Should provide insuficient funds message | Found as per expectation. | 1500 | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button 4.Enter account number 5.Click Ok |  |  | Passed
44 |  |  |  | Transfer with empty | Should provide insuficient funds message | Found as per expectation. |  | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button 4.Enter account number 5.Click Ok |  |  | Passed
45 |  |  |  | Transfer with text input | Should provide invalid amount or target account | Found as per expectation. | sadfdsf | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on Transfer button 4.Enter account number 5.Click Ok |  |  | Passed
66
67
69 |  |  | Add Interest | Add interest button is clickable | Should be clickable | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click add interest button |  |  | Passed
70 |  |  |  | Add interest with zero balance | Should not increase balance | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click add interest button |  |  | Passed
71 |  |  |  | Add interest with zero balance | Should insuficient balance message | Found not as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click add interest button | https://prnt.sc/Ga1DqkbnbykO |  | Failed
72 |  |  |  | Add interest to balance | Should increases by interest rate (e.g., 5%) | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click add interest button |  |  | Passed
|  |  |  | Add interest multiple times | Should increases by interest rate (e.g., 5%) | Found as per expectation. | N/A | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click add interest button |  |  | Passed
|  |  | Reset Account | Reset Account Button is clickable | Should be clickable | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | Reset Account button ask permission to reset | Should ask permission | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | Reset account clears balance | Should clear balance | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | Reset clears transaction history | Should clear history | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | Reset with already empty account | Should clear balance | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | After reseting show message | Should provide message | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | Reset User1 Acoount | Should reset only user1,not other user | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | Reset User1 Acoount | Should not effect user2 | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
|  |  |  | Reset User Acoount | Should not effect user1 | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click Reset Account |  |  | Passed
Passed
|  |  | Transactions History | Transaction recorded after deposit | Should record deposit amount | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Transaction details after deposit | Should record time,date | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Transaction recorded after withdrawal | History shows withdrawal entry | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Transaction recorded after transfer | Should record transfer amount | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Transfer account details recorded after transfer | Should record Transfer account details | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Preview transaction history | Should preview history properly | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | History cleared after reset | Should clear History section | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  | Transfer History | Validate transfer history timestamp format | Should preview timestamp format | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to transfer history |  |  | Passed
|  |  |  | Validate history not updated on failed transfer | Should not updated transfer details | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to transfer history |  |  | Passed
|  |  |  | Transfer amount exceeds User1 balance | Should not record transfer history | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to transfer history |  |  | Passed
|  |  | Filter Transactions | No filter is applied. | Should displayed all transactions | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Applied deposit filter | Should displayed only deposited transactions | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Applied withdrawals filter | Should displayed only withdrawals transactions | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Applied transfer filter | Should displayed only transfer transactions | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  |  | Applied All filter | Should displayed all transactions | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Go to filter transcations |  |  | Passed
|  |  | Toggle dark Mode | Validate toggling between light and dark mode | Should shift to dark mode | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on toggle dark mode |  |  | Passed
|  |  |  | Validate toggling back to light mode | Should shift to light mode | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on toggle dark mode |  |  | Passed
|  |  |  | visibility of text, buttons, and input fields in dark mode | Should preview properly | Found as per expectation | None | 1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click on toggle dark mode |  |  | Passed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Banking System
Module Name | [5 empty] | Total No. | Status
Feature Name | Deposit,Withdraw,Transfer,Add Interest,Reset Account,Transfer History,Transaction History,Filter Transactions
Test Case Version | 1 |  |  |  |  | 62 | PASS
Written By | Akram Khan |  |  |  |  | 1 | FAIL
Executed By | Akram Khan |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 62 | 1 | 0 | 0 | 63
Grand Total | 62 | 1 | 0 | 0 | 63
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01
Issue: Add interest with zero balance
Reproducing Steps:
1.Go to browser 2.Search https://testing-and-learning-hub.vercel.app/Projects/Bank%20System/bank_system.html 3.Click add interest button
Env: Production
Module: Transactions
Priority: Low
Severity: Minor
https://prnt.sc/Ga1DqkbnbykO
Responsible QA: Akram Khan

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (63/63)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/63)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (62/63)*100 = 98%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (1/63)*100 = 2%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/63)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A